# School of Computer Science Engineering and Technology

Course- B.Tech                                              	Type- Elective-II

Course Code- CSET-324          			Course Name: Software Project Management

Year-   2025-26                                                           Semester- ODD

## Lab Assignment  – Cross-Functional Planning with Advanced Roadmaps

## CO-Mapping

| Exp. No. | Name | CO1 | CO2 / CO3 |
| --- | --- | --- | --- |
| 11 | Cross-Functional Planning with Advanced Roadmaps: Portfolio Roadmaps, Projects, and Releases | ✅ | ✅ |

### Objective:

### To perform cross-functional project planning using Jira Advanced Roadmaps.

### To visualize and manage work across multiple teams and projects with dependencies and timelines.

### To understand how Advanced Roadmaps support coordination, release planning, and progress tracking.

### Project Scenario

A university is developing a College Event Management Suite, which includes:
- College Event App (CEA) – for students to register and participate in events.
- Event Admin Portal (EAP) – for organizers to approve, schedule, and publish results.
There are four cross-functional teams involved: Developers, Testers, UX Designers, DevOps Engineers. Your task is to simulate the project planning, release coordination, and portfolio roadmap for both projects using Swanly integrated with Jira Cloud.

### Task 1: Install Swanly App in Jira

1. Go to Apps → Explore more apps → Search “Swanly”.
2. Select “Swanly: Portfolio Roadmaps Structure Gantt, Release Timeline” by Appfire.
3. Click “Try it free / Install” and confirm the installation.

### Task 2: Create Two Jira Projects

| Project | Description | Key |
| --- | --- | --- |
| College Event App | Student-facing mobile application | CEA |
| Event Admin Portal | Admin dashboard for organizers | EAP |

Each project should be created using the Scrum Template.

### Task 3: Define Epics and Stories

Epic → Story/Task → Sub-task.

Project A (CEA): College Event App (Student-facing)

Epic A1: Student Registration & Login

- Goal: Students sign up/login to app

- Dates: 04 Nov → 22 Nov 2025

- Issues:

  - CEA-101 Story — Design login & signup screens (UX)

    - Story points: 3; Assignee: UX; Dates: 04 Nov → 07 Nov

    - Sub-task: CEA-101a Create Figma wireframes (04 Nov → 05 Nov)

  - CEA-102 Story — Implement auth API integration (DEV)

    - Story points: 5; Assignee: Dev; Dates: 08 Nov → 14 Nov

    - Depends on CEA-101 (UX screens)

  - CEA-103 Story — QA: Auth flow test cases & execution (QA)

    - Story points: 3; Assignee: QA; Dates: 15 Nov → 18 Nov

    - Depends on CEA-102

  - CEA-104 Task — CI pipeline for mobile build (DEVOPS)

    - Story points: 2; Assignee: DevOps; Dates: 11 Nov → 13 Nov

Epic A2: Event Discovery & Booking

- Dates: 25 Nov → 13 Dec 2025

- Issues:

  - CEA-201 Story — Browse events UI (UX) — 25 Nov → 27 Nov — SP: 3

  - CEA-202 Story — List events API + pagination (DEV) — 28 Nov → 04 Dec — SP: 5 — depends on CEA-201

  - CEA-203 Story — Register for event + confirmation (DEV) — 05 Dec → 10 Dec — SP: 5 — depends on CEA-202

  - CEA-204 Story — QA booking flow (QA) — 11 Dec → 13 Dec — SP: 3 — depends on CEA-203

Project B (EAP): Event Admin Portal (Organizer/Admin-facing)

Epic B1: Admin Approvals & Scheduling

- Dates: 04 Nov → 06 Dec 2025

- Issues:

  - EAP-101 Story — Admin dashboard skeleton (DEV) — 04 Nov → 08 Nov — SP: 3

  - EAP-102 Story — Approve/reject registrations (DEV) — 10 Nov → 17 Nov — SP: 5 — depends on EAP-101

  - EAP-103 Story — Schedule management UI (UX) — 11 Nov → 14 Nov — SP: 3

  - EAP-104 Story — QA regression pass (QA) — 03 Dec → 06 Dec — SP: 3 — depends on EAP-102, EAP-103

Epic B2: Results & Notifications

- Dates: 25 Nov → 18 Dec 2025

- Issues:

  - EAP-201 Story — Results publishing service (DEV) — 25 Nov → 02 Dec — SP: 5

  - EAP-202 Story — Push/email notifications (DEVOPS) — 03 Dec → 09 Dec — SP: 3 — depends on EAP-201

  - EAP-203 Story — QA: Notifications & results (QA) — 16 Dec → 18 Dec — SP: 3 — depends on EAP-202

Assign each issue to your teammates (or to yourself) and add the labels (UX/DEV/QA/DEVOPS). Add Start and Due dates as above.

Task 4: Create Sprints (Scrum cadence)

- Sprint 1: 04 Nov → 15 Nov 2025

  - Target issues: CEA-101, CEA-102, CEA-104, EAP-101, EAP-102, EAP-103

- Sprint 2: 18 Nov → 29 Nov 2025

  - Target issues: CEA-103, CEA-201, EAP-201

- Sprint 3: 02 Dec → 13 Dec 2025

  - Target issues: CEA-202, CEA-203, EAP-202, EAP-104

- Mini-sprint 4: 16 Dec → 18 Dec 2025

  - Target issues: CEA-204, EAP-203

Task 5: Build the portfolio roadmap in Swanly (step-by-step)

- Open Swanly → Roadmaps → Create Roadmap.

- Add projects: select CEA and EAP (multi-project plan).

- Timeline (Gantt view): switch to Month/Week zoom; group by Project or by Label (to see DEV/QA/UX/DEVOPS swimlanes).

- Drag Epics/Stories to match the dates above (or set dates in the right panel).

- Add dependencies:

  - CEA-101 → CEA-102 → CEA-103

  - CEA-201 → CEA-202 → CEA-203 → CEA-204

  - EAP-101 → EAP-102; EAP-201 → EAP-202 → EAP-203

- Filters: create quick filters like label = QA or “Project = CEA”.

- Save the roadmap view (for sharing/stakeholders).

Task 6: Create the Cross-Project Release in Swanly

- Swanly → Releases → New Cross-Project Release

- Name: R1 – Winter Fest 2025

- Dates: 04 Nov → 19 Dec 2025

- Select projects & link versions: CEA v1.0, EAP v1.0

- Save.

You’ll now see one consolidated release with scope (stories/time), status, and burndown, synchronized across both projects.

Task 7: Track progress (daily/weekly)

- Team members update issue Status and Remaining Estimate / Time Spent in Jira.

- In Swanly → Releases → R1, open:

  - Release Burndown (work remaining vs time)

  - Issue/Release list (status, SP, time)

- In Swanly → Roadmap, watch slippages and dependency impacts.

### Task 8: Reporting & Dashboard

Take screenshots of the following:
1. Swanly Roadmap (Gantt View) showing dependencies.
2. Cross-Project Release (R1 – Winter Fest 2025).
3. Release Burndown Chart.
4. Issue List / Scope View.
5. Jira Dashboard showing sprint or team progress.

### Submission Instructions

Submit your assignment on the LMS.

Expected Output

- Successfully created multi-project roadmap using Swanly.
- Visualized dependencies and team workload.
- Monitored release progress via burndown chart.
- Demonstrated coordination between multiple cross-functional teams.